## Slide 1: Level 4 Project
Week 9 Meeting
(Week 8 Recap)

## Slide 2: Completed work
Dissertation work: reviewed research done on using autoencoders for dimensionality reduction
Moved code to Colab
A lot of autoencoder tuning: attempts at...
  Resizing dataset
  Scaling values
  Visualising filters
  Adding layers
  Changing layer parameters
  Adding normalisation post-activation
  Relu vs leakyrelu
  Trying autoencoder on MNIST dataset
Kept track of (most) progress in presentation

## Slide 3: Completed work
Solution?: image preprocessing with edge detectors
  Tested how to make the cells pop out more with Fiji ImageJ
  Replicated that in code:
    Used a sobel filter
  Getting some more promising results
    But still not ideal
    Attempted to get better quality: stagnating loss

## Slide 4
Unstimulated, conA, empty well (validation set)

## Slide 5: Questions
Quick recap:
  We want to use autoencoder to learn reduced version of the cell images
  And use that in a clustering/visualisation algorithm like t-sne?
Dataset:
  Even smaller images?
  Would it be better to calculate the overlap first, then compress?
  Should I do data augmentation?
Running through algorithm:
  Train/test/validation split

## Slide 6: Rough plan for semester, reworked
Week 8
  Clean up code!
  More dimensionality reduction in the encoded images
  Apply chosen clustering algorithm
  Tune clustering algorithms to improve performance
Week 9
  Tuning autoencoder to get good images even with reduced dimensionality
  If no improvement, work on image pre-processing again
Week 10
  Final autoencoder tuning if needed
  Run through clustering algorithm