## Slide 1: Level 4 Project
Week 5 Meeting
(Week 4 Recap)

## Slide 2: Completed work
Tuned autoencoder
  Followed tutorial on visualising filters
  Tweaked code according to results
Current network architecture:
  More filters in the convolutional layers
  MaxPooling is done with 1x1 stride rather than 2x2, givs better results

## Slide 3
With pool size (2,2) instead of (1,1) – some tweaking to be done for speed

## Slide 4: Questions
Should I keep a copy of the outputs whenever I change a parameter? --> for dissertation
The compressed representation should be lower size than original image, for speed?
Should I look to get resized images in a new directory?
Uploading files online for access to Google Colab?
In the future, if we want this to be a tool: should I make different python scripts that would be runnable in the Terminal, on top of the jupyter notebooks?
  They’re more convenient for me, but might not be for a user

## Slide 5: Rough plan for semester 1 (unchanged)
(potentially to be reworked following my questions)
Week 4
  Tuning autoencoder
Week 5
  Tuning autoencoder
Week 6
  HPC training day (hopefully will help with running some models)
  Calculate overlap of images
Week 7
  Start working on clustering algorithm for image overlaps
Week 8
  Tune clustering algorithm
Week 9
  Label t-cell/dendritic cells images:
  Evaluate clustering performance